## Request log
[10 empty] | Lifts Not Listed |  | Business Support Process Notes
Date received | Time Received | Request from | Lift location detail | Lift ref number | Fault | BSO | Status | Last Updated | Contractor | Date reported to contractor | Time reported to contractor | Report reference / Works order | Notes
2023-11-15 | 11:00 | Theo Theodoris, | Cumberland House 45/84 Centre | M22918 | Intermittent fault and doors screech every time the door opens and closes. Lift taken out of service by Lift Contractor 15.11.23 due to faulty car door rollers. RBK has requested that the contractor puts the lift back into service 16.11.23 in the afternoon pending planned attendance to replace the rollers on 20.11.23. Axis Customer Services - please do not raise call outs for this issue until the parts have been replaced. | Dave | Outstanding | 2023-11-17 | RJ Lifts | 2023-11-15 | 12:10 | WO00964069 RJ Lifts ref 393131 | Reported by email to RJ Lifts cc SP PD LB TT BS 16.11.23 Update from RJ Lifts: 15/11/2023 14:10 Upon arrival found the lift in serivce, after investigation found d landing lock fault, adjusted and tested, traced noise back to car door rollers, lift has been isolated for new car door rollers, lift left out of service. Planned attendance 20.11.23 16/11/23 SP update - I have just spoken to RJ about this. The screeching noise was due to the door rollers being worn so the lift was isolated last night and new rollers were ordered. I have been given a provisional date of 20/11 for them to arrive and for the repair. Due to this and the recent long term lift outage at this block I have asked for the lift to be put back into service this afternoon. In my opinion screeching doors is better than no lift at all. BS, please be aware of this in case any residents call up.
2023-11-21 | 08.55 | Anthonia Shodiya | Fordham House/Connington | M22910 | Hole under flooring inside lift and the lift stops on the 2nd floor and jolts, does not go up to the third floor. Lift has been turned off for repair. | Tina | Outstanding | 2023-11-22 | RJ Lifts | 2023-11-21 | 10.02 | WO00964499 RJ ref 393978 | Emailed RJ lifts
2023-11-21 | 08.55 | Anthonia Shodiya | Madingley House Goods/Pass EPGL Evens Lift | M22902 | Even lift - door opens - however the opening button inside the lift is stuck needs to be rectified. | Tina | Outstanding | 2023-11-22 | RJ Lifts | 2023-11-21 | 10.30 | WO00964504 RJ ref 393992 | Emailed RJ lifts
|  |  |  | #N/A |  |  |  |  | #N/A
|  |  |  | #N/A |  |  |  |  | #N/A
|  |  |  | #N/A |  |  |  |  | #N/A
|  |  |  | #N/A |  |  |  |  | #N/A
|  |  |  | #N/A |  |  |  |  | #N/A

## Requests Resolved_Superseded
N.B. Purchase order number for all Rubax lift faults : 31014992 |  |  |  | Rubax main repairs number : 01925 849200 or Freephone: 0800 7318277 | [5 empty] | Lifts Not Listed |  |  | Business Support Process Notes
Date received | Time received | Request from: | Lift location detail | Lift ref number | Fault | BSO | Status | Updated | Contractor | Date reported to contractor | Time reported to contractor | Report reference / Works order | Notes
2023-04-26 | 16:40 | Axis CC | Croxton House Passenger EPL | 21693 M22907 | Reported and repaired on 24th now not working again | Stuart P | Resolved |  | Rubax (until May 2024) | 2023-04-26 | 16:45 | 593707 | Resident from Oakington block reported fault to Axis CC
2023-05-02 | 14:38 | Axis CC | Fountain Court | M22926 | Lift is working but is apparently making a lot of noise. Gooding Close, New Malden, Surrey, KT3 5DH | Dave | Resolved |  | RJ Lifts | 2023-05-02 | 15:50 | WO 0094 7793 | Reported by Nadine Clappison HOP via Axis. Lift is working but is apparently making a lot of noise. 05/05/2023: Danny spoke to RJ lifts this afternoon, ref is 333 777 and they said there should be someone there within the next 4 hours.
2023-05-03 | 14:45 | Contact Centre/Tenant | Cambridge Gardens Estate 125/160 EAST | M22915 | Lift out | Danny | Resolved |  | RJ Lifts | 2023-05-03 | 15:35 | WO 0094 7887 | Lift reported as faulty by multiple residents - Engineer attedning 03/05/23. Awaitng parts - on order 04/05/2023 update from RJ Lifts Contracts Manager: lift is in service
2023-05-03 | 14:50 | Contact Centre/Tenant | Cambridge Gardens Estate 105/124 NORTH | M22914 | Lift out | Danny | Resolved |  | RJ Lifts | 2023-05-03 | 15:35 | WO 0094 7888 | Lift reported as faulty by multiple residents - Engineer attending 03/05/23. Engineer reported lift was working on arrival. 04/05/2023 update from RJ Lifts Contracts Manager - has had an intermittent fault has been attended today and is back in service
2023-04-27 | 8:35 | Contact Centre/Tenant | Cambridge Gardens Estate 67/102 CENTRE | M22913 | Lift out | Dave | Resolved |  | RJ Lifts | 2023-04-27 | 10:39 | WO 0094 7468 | Awaiting parts - on order (Needs new landing lock set and hanging roller). Dave spoke to RJ Lifts 04/05/2023 and was informed lead time for delivery of parts is 1 to 2 weeks. 04/05/2023 update from RJ Lifts Contracts Manager: quote sent to RBK for parts, member of staff dealing with.Update from Rob - awiting quote for approval.
2023-04-20 | 16:00 | Contact Centre/Tenant | Cambridge Gardens Estate 17/64 WEST | M22912 | Lift out | Dave | Resolved |  | RJ Lifts | 2023-04-20 | 16:27 | WO 0094 6955 | Awaiting parts - on order (Needs new hangar rollers ) 04/05/2023: update from RJ Lifts Contracts Manager - The parts for that are being delivered tomorrow and the lift will be back in service tomorrow / Saturday.
2023-05-03 | 15:20 | Axis | Canbury Court 7/42 | M22932 | Lift out | Rachel | Resolved |  | RJ Lifts | 2023-05-03 | 16:10 | WO 00947896 | Lift back in service as of 9pm 04/05/23
2023-05-04 | 8:24 | Estate Services | Cambridge Gardens Estate 105/124 NORTH | M22914 | "The North wing lift is down again as of 8am". Second breakdown in 24 hours. | Danny | Resolved |  | RJ Lifts | 2023-05-04 | 8:42 | WO 0094 7918 | Reported to RJ lifts. Engineer should go out today. Dave spoke to RJ lifts @ 3.15 pm 4/5, technician has had to leave the lift isolated and will 'return'. :Lift is back in service
2023-05-04 | 12:00 | Axis CC | Cumberland House 45/84 Centre | M22918 | Resident of number 45 Cumberland House reports he lift is out of service M22918. | Dave | Resolved |  | RJ Lifts | 2023-05-04 | 12:40 | WO 0094 7956
2023-05-09 | 6:55 | Axis CC | Cambridge Gardens Estate 105/124 NORTH | M22914 | "This lift is down again" | Danny | Resolved |  | RJ Lifts | 2023-05-09 | 8:42 | WO 0094 8160 | Reported faulty by Theo
2023-05-10 | 13:53 | Contact Centre/Tenant | Cambridge Gardens Estate 105/124 NORTH | M22914 | "Tenant called to report the North Wing lift (M2291) is no longer working" | Danny | Resolved |  | RJ Lifts | 2023-05-10 | 16:57 | WO 0094 8355 | Engineer will attend this evening 10/05/23
2023-05-11 | 16:12 | Axis CC | Croxton House Passenger EPL | 21693 M22907 | "Tenant called to report the lift that was repaired today is no longer working" | Danny | Resolved |  | Rubax (until May 2024) | 2023-05-11 | 18:33 |  | Reported to Stuart Pike Thursday eve
2023-05-11 | 16:45 | Axis CC | Cambridge Gardens Estate 17/64 WEST | M22912 | "Tenant has called to report the lift is out of service again. " | Danny | Resolved |  | RJ Lifts | 2023-05-11 | 17:57 | WO 0094 8458 | Reported to RJ lifts at 17:57. Engineer should attend this evening
2023-05-16 | 11:18 | Estate Services | Cambridge Gardens Estate 105/124 NORTH | M22914 | "This lift is down again" | Danny | Resolved |  | RJ Lifts | 2023-05-16 | 13:45 | WO 0094 9083 | Reported to RJ lifts by phone at 13:45. Engineer will attend today.
2023-05-18 | 10:27 | Estate Services | Cambridge Gardens Estate 17/64 WEST | M22912 | This lift is out of service | Dave | Resolved |  | RJ Lifts | 2023-05-18 | 11:23 | WO00949041 | Reported by email to RJ Lifts cc SP,PD,LB Theo ESO, cc BS
2023-05-18 | 13:24 | Estate Services | Cambridge Gardens Estate 125/160 EAST | M22915 | This lift has nasty smell from something in the shaft. Possibly under the lift. | Dave | Resolved |  | RJ Lifts | 2023-05-18 | 15:00 | WO00949070 | Reported by email to RJ Lifts cc SP,PD,LB Theo ESO, cc BS
2023-05-25 | 12:51 | Tom Dalton | Dowler Court | TBA | Alarm sounding in lift. Needs to be dealt with urgently as one tenant has a pre surgery appointment tomorrow. | Dave | Resolved |  | RJ Lifts | 2023-05-25 | 14:50 | WO00949605 | Reported by phone to Kerry Pike of RJ Lifts as no lift code + by email to RJ Lifts cc SP,PD,LB Tom HO, cc BS
2023-06-05 | 9.52 | Contact Centre/Tenant | Fordham House/Connington | M22910 | the Fordham lift isn't working. Could you possibly arrange repairs. | Rachel | Resolved |  | RJ Lifts | 2023-06-05 | 10.15 | WO00950283 | Reported by email to RJ Lifts cc SP,PD,LB cc OO. 06/06/2023 further reported by Tracey Harrison of the Contact Centre. Update from Stuart Pike 6/6/23: This was reported as an entrapment on 03/06 and parts were required. RJ Lifts will be back on site tomorrow. In the meantime the resident could walk across Fordham block to use the Chippenham lift.
2023-06-06 | 12.24 | Axis | Glenbuck Court | M22919 | Light in lift is not working | Tina | Resolved |  | RJ Lifts | 2023-06-06 | 14.23 | WO00950439 | Reported to RJ Lifts by email
2023-06-08 | 13:32 | Contact Centre/Tenant | Madingley House Goods/Pass EPGL Odds Lift | 21689 M22903 | Lift is not working | Dave | Resolved |  | Rubax (until May 2024) | 2023-06-08 | 14:50 | n/a | Reported to Rubax by phone. Confirmed to contact centre by email cc SP,PD,LB
2023-06-13 | 7.25 | Theo Theodoris | Cambridge Gardens Estate 17/64 WEST | M22912 | Light in lift is not working | Tina | Resolved |  | RJ Lifts | 2023-06-13 | 8.38 | WO00950898 | Reported to RJ Lifts by email
2023-06-13 | 11:18 & | Axis | Glenbuck Court | M22919 | An elderly resident has reported the lift is not working at Glenbuck Court KT6 6BY. She was unable to gibe me the lift number but said she lives at property number 32 and it is the lift closest to her property. is not working. The resident has a disability so unable to get out of the block without a working lift. | Sarah | Resolved |  | RJ Lifts | 2023-06-13 | 12:27 | WO00950955 | Reported to RJ Lifts by email
2023-06-13 | 11:43 | Axis | Glenbuck Court | M22919 | Resident of number 10 has reported the lift for numbers 1-16 Glenbuck Court | Sarah | Resolved |  | RJ Lifts | 2023-06-13 | 12:27 | WO00950955 | Reported to RJ Lifts by email
2023-06-13 | 12:08 | Axis | Glenbuck Court | M22919 | Fault: Lift is not responding | Sarah | Resolved |  | RJ Lifts | 2023-06-13 | 12:27 | WO00950955 | Reported to RJ Lifts by email
2023-06-14 | 7.38 | Estate Services | Cambridge Gardens Estate 67/102 CENTRE | M22913 | Lift is out of service. Please arrange a repair | Rachel | Resolved |  | RJ Lifts | 2023-06-14 | 8.33 | WO 00950996 | Reported to RJ lifts by email, cc'd SP, LB PD & TT (estates).
2023-06-14 | 9.43 | Housing Officer | Madingley House Goods/Pass EPGL Evens Lift | 21688 M22902 | Both lifts reported out at Madingley | Rachel | Resolved |  | Rubax (until May 2024) | 2023-06-14 | 9.51 | n/a | Reported to RUBAX via phone ref: 600383
2023-06-14 | 9.51 | Housing Officer | Madingley House Goods/Pass EPGL Odds Lift | 21689 M22903 | Both lifts reported out at Madingley | Rachel | Resolved |  | Rubax (until May 2024) | 2023-06-14 | 9.51 | n/a | Reported to RUBAX via phone ref: 600383
2023-06-14 | 9.51 | Axis | Cambridge Gardens Estate 105/124 NORTH | M22914 | The resident of number 104 reports the lift is out of service. (M22914) Please arrange for a lift engineer to attend | Rachel | Resolved |  | RJ Lifts | 2023-06-14 | 10.4 | WO 00951011 | Reported to RJ Lifts via email cc'd SP, LB PD and Axis cc's
2023-06-16 | 16.52 | Axis | Glenbuck Court | M22919 | Lift is working on and off and lift light not working | Tina | Resolved |  | RJ Lifts | 2023-06-19 | 14.45 | WO00951427 | Reported to RJ lifts by emal
2023-06-19 | 17:00 | Axis | Westwick House | M22908 | "the several bottoms on the lift have been broken" | Danny | Resolved |  | RJ Lifts | 2023-06-20 | 10:30 | WO 0095 1468 | Reported to RJ lifts by email
2023-06-20 | 9:18 | Aaron Povey | Impington House Passenger EPL | 21692 M22906 | "The lift has broken down on the 3rd floor, the doors will not close properly" | Danny | Resolved |  | Rubax (until May 2024) | 2023-06-20 | 11:50 | N/A | Reported to Rubax via phone, engineer will attend tomorrow (21/06/2023)
2023-06-20 | 10:38 | Contact Centre/Tenant | Croxton House Passenger EPL | 21693 M22907 | Top floor is not moving, doors shut and no light showing says " lift out of service" | Rachel | Resolved |  | Rubax (until May 2024) | 2023-06-20 | 11:00 | 600666 | Reported to Rubax via phone call. Ref: 600666 - Rubax advised there was a call out last week for this lift but cannot find any updates, will be chasing up. Emailed SP and CC contact centre
2023-06-20 | 10:38 | Contact Centre/Tenant | Impington House Passenger EPL | 21692 M22906 | This lift in block also down | Rachel | Resolved |  | Rubax (until May 2024) | 2023-06-20 | 11:00 | 60067 | Reported to Rubax via same phone call as above.. Ref: 600667 - Rubax advised they will send engineer to look at both Impington/Croxton. emailed SP and CC contact centre
2023-06-20 | 16:24 | RBK/Stuart Pike | Duxford House Passenger EPL | 21695 M22909 | The lift is out of service | Danny | Resolved |  | Rubax (until May 2024) | 2023-06-20 | 16:50 | N/A | Reported to Rubax via phone call as urgent, requested out of hours engineer this evening
2023-06-22 | 9:10 | Axis | Croxton House Passenger EPL | 21693 M22907 | The lift is out of action | Danny | Resolved |  | Rubax (until May 2024) | 2023-06-22 | 9:55 | 600786 | Reported to Rubax via phone call, ref 600786. Needs a part which is arriving for repair on 22/06/2023. Update: Croxton now back in service as of 14:00 22/06/2023
2023-06-22 | 10:14 | Axis | Impington House Passenger EPL | 21692 M22906 | The lift is down | Danny | Resolved |  | Rubax (until May 2024) | 2023-06-22 | 12:55 |  | Reported to Rubax via phone call. Engineer reported lift has been vandalised with a screw. Needs a technical engineer to attend, waiting for update
2023-06-22 | 10:14 | Axis | Madingley House Goods/Pass EPGL Odds Lift | 21689 M22903 | The lift is down | Danny | Resolved |  | Rubax (until May 2024) | 2023-06-22 | 12:55 |  | Reported to Rubax via phone call. Needs a technical engineer to attend, waiting for update
2023-06-22 | 10:51 | Axis | Glenbuck Court | M22919 | Lift is out of service | Danny | Resolved |  | RJ Lifts | 2023-06-22 | 13:50 | WO 0095 1645 | Reported to RJ lifts by email
2023-06-22 | 10:09 | Axis | Westwick House | M22908 | Lift is down | Danny | Resolved |  | RJ Lifts | 2023-06-22 | 14:25 | WO 0095 1651 | Reported to RJ lifts by email
2023-06-22 | 15:58 | RBK/Fire Brigade | Graveley House Goods/Pass EPGL Evens Lift | 21691 M22905 | Lift has been taken out of service by fire brigade | Danny | Resolved |  | Rubax (until May 2024) | 2023-06-22 | 16:35 |  | Reported to Rubax via phone call, but they were already aware - an engineer is already onsite working on the lift
2023-06-22 | 17.04 | Axis | Glenbuck Court | M22919 | Lift not working | Tina | Resolved |  | RJ Lifts | 2023-06-23 | N/A | N/A | Reported to Stuart Pike as there is an ongoing issue with lift. The lift was left off on the 22/6 due to an intermittent fault and will be attended by a technical engineer today 23/6
2023-06-23 | 8:16 | Theo Theodoris | Cambridge Gardens Estate 105/124 NORTH | M22914 | Lift keeps jamming on 4th floor | Dave | Resolved |  | RJ Lifts | 2023-06-23 | 8:48 | WO 0095 1706 | Reported to RJ lifts by email cc SP, PD, LB
2023-06-26 | 8.14 | Theo Theodoris | Cambridge Gardens Estate 125/160 EAST | M22915 | Lift is out of service | Tina | Resolved |  | RJ Lifts | 2023-06-26 | 8.36 | WO 00951833 | Reported to RJ lifts by email
2023-06-26 | 11:02 | Axis/Caretaker | Duxford House Passenger EPL | 21695 M22909 | Lift gets stuck on the 2nd floor and then when it does go down it stops before it gets to the ground level and opens before the lift is level with the ground. | Danny | Resolved |  | Rubax (until May 2024) | 2023-06-26 | 12:40 | N/A | Reported to Rubax via phone. Ref: 600 990
2023-06-26 | 11:02 | Axis/Caretaker | Impington House Passenger EPL | 21692 M22906 | Lift is stuck on the 3rd floor – doors are stuck open at the moment. | Danny | Resolved |  | Rubax (until May 2024) | 2023-06-26 | 12:40 | N/A | Reported to Rubax via phone. Ref: 600 991
2023-06-28 | 16:12 | Axis | Croxton House Passenger EPL | 21693 M22907 | Resident called to report lift is out of service. Door is open on the ground floor. | Rachel | Resolved |  | Rubax (until May 2024) | 2023-06-28 | 16:30 | N/A | Reported to Rubax via phone; Ref: 601180 - Advised, will try to get evening engineer to look at tonight or will be tomorrow.
2023-07-03 | 12:54 | Axis | Impington House Passenger EPL | 21692 M22906 | Resident at no.20 has reported that the lift is out 2 days after being fixed. | Sarah | Resolved |  | Rubax (until May 2024) | 2023-07-03 | 14:16 | N/A | Reported to Rubax via phone. Ref: 603798
2023-07-05 | 15:18 | Paul Dunkerton | Croxton House Passenger EPL | 21693 M22907 | The Croxton lift has been out since Monday, the far one out since this morning, I think,, now the one in the middle is out of order! | Rachel | Resolved |  | Rubax (until May 2024) | 2023-07-05 | 15:40 | N/A | Reported to Rubax by phone ref: 603911 Engineer being sent to investigate 3 lifts.
2023-07-05 | 14:34 | Axis | Westwick House | M22908 | Lift not responding | Rachel | Resolved |  | RJ Lifts | 2023-07-05 | 16:05 | WO00952590 | Reported to RJ via email inc cc axis Sp LB PD . 07/07/2023 SP -This lift has already been reported and is awaiting new push buttons to be delivered and fitted.
2023-07-10 | 7.58 | Theo Theodoris | Cambridge Gardens Estate 125/160 EAST | M22915 | Out of service | Tina | Resolved |  | RJ Lifts | 2023-07-10 | 8.3 | WO00952930 | Reported to RJ lifts by email
2023-07-10 | 9:33 | Sam Hogan -RBK | Edinburgh Court | No code | Lift out of action, stopped working yesterday | Sarah | Resolved |  | RJ Lifts | 2023-07-10 | 10:30 | WO00952952 | Reported to RJ lifts by email
2023-07-12 | 12.11 | Sam Horgan | Hugh Herland House | AC754 | Fix lift button on ground floor as it has come out of it's housing. | Tina | Resolved |  | RJ Lifts | 2023-07-12 | 12.34 | WO00953146 | Reported to RJ lifts by email
2023-07-13 | 12:08 | Axis | Glenbuck Court | M22919 | Lift is acting up | Danny | Resolved |  | RJ Lifts | 2023-07-12 | 13:31 | WO 0095 3267 | Reported to RJ lifts by email
2023-07-13 | 17.33 | Stuart PIke | Duxford House Passenger EPL | 21695 M22909 | Not working | Tina | Resolved |  | Rubax (until May 2024) | 2023-07-13 | Not known | N/A | Stuart Pike reported fault direct with Rubax engineer due to attend 13/07/23
2023-07-13 | 17.33 | Stuart PIke | Impington House Passenger EPL | 21692 M22906 | Not working | Tina | Resolved |  | Rubax (until May 2024) | 2023-07-13 | Not known | N/A | Stuart Pike reported fault direct with Rubax engineer due to attend 13/07/23
2023-07-13 | 17.33 | Stuart PIke | Croxton House Passenger EPL | 21693 M22907 | Not working | Tina | Resolved |  | Rubax (until May 2024) | 2023-07-13 | Not known | N/A | Stuart Pike reported fault direct with Rubax engineer due to attend 13/07/23
2023-07-17 | 9:40 | Stuart PIke | Glenbuck Court | M22919 | Ongoing issue lift getting stuck | Rachel | Resolved |  | RJ Lifts | 2023-07-17 | 12.05 | WO00953602 | Reprted to RJ lifts byb email, cc PD, LB & Adam Kendall (RJ lifts)
2023-07-18 | 16:41 | Stuart PIke | Croxton House Passenger EPL | 21693 M22907 | Lift failure | Danny | Resolved |  | Rubax (until May 2024) | 2023-07-18 | 17:55 | RX 3079 | Reported to Rubax via phone, engineer will attend tonight
2023-07-18 | 16:41 | Stuart PIke | Duxford House Passenger EPL | 21695 M22909 | Lift failure | Danny | Resolved |  | Rubax (until May 2024) | 2023-07-18 | 17:55 | RX 3080 | Reported to Rubax via phone, engineer will attend tonight
2023-07-19 | 7:54 | Estate Services | Cambridge Gardens Estate 67/102 CENTRE | M22913 | The door close button in the lift panel is damaged. | Rachel | Resolved |  | RJ Lifts | 2023-07-19 | 8:30 | WO00953743 | Reported to RJ Lifts via email cc'd SP, LB PD and ESO. 19/07/2023: report from RJ Lifts - Upon arrival found the lift in service, found door open button pushed through and damaged, returning with a 2nd engineer to release the cop to further investigate, hole blanked over awaiting return visit
2023-07-19 | 8:35 | Estate Services | Cambridge Gardens Estate 125/160 EAST | M22915 | Lift is out of service | Rachel | Resolved |  | RJ Lifts | 2023-07-19 | 8:45 | WO00953747 | Reported to RJ Lifts via email cc'd SP, LB PD and ESO.
2023-07-19 | 16:23 | Axis | Childerley House Goods/Pass EPGL Odds Lift B | 21687 M22901 | "Lift out of order for the last week" | Danny | Resolved |  | Rubax (until May 2024) | 2023-07-20 | 10:45 | 605010 | Reported to Rubax via phone, engineer will attend
2023-07-20 | 12:08 | Stuart Pike | Croxton House Passenger EPL | 21693 M22907 | Lift failure reported via Olly Whering |  | Resolved |  | Rubax (until May 2024) | 2023-07-20 | 12:08 | 605015 | Reported to Rubax. Lift was only put back into service on 19/07 @ 3pm and failed @ 8pm
2023-07-20 | 12:24 | Axis | Glenbuck Court | M22919 | Report of the light not working in the centre lift | Dave | Resolved |  | RJ Lifts | 2023-07-20 | 13:43 | WO00953865 | Reported to RJ Lifts via email cc'd SP, LB PD and Axis
2023-07-20 | 16:41 | Stuart Pike | Glenbuck Court | M22919 | The emergency call button inside the lift car does not dial anywhere. it is supposed to call RJ lifts directly incase if an emergency entrapment. | Dave | Resolved |  | RJ Lifts | 2023-07-21 | 8:59 | WO00953948 | Reported to RJ lifts by email cc SP, PD, LB
2023-07-21 | 14:21 | Contact Centre/Tenant | Childerley House Goods/Pass EPGL Odds Lift B | 21687 M22901 | "Lift has not been working for the last 2 weeks" | Danny | Resolved |  | Rubax (until May 2024) | 2023-07-21 | 14:35 | N/A | Reported to Rubax via phone. Engineer has attended already today and hopes to go back later, likely that a technical engineer is needed
2023-07-24 | 12:24 | Axis | Impington House Passenger EPL | 21692 M22906 | "Lift not working" | Rachel | Resolved |  | Rubax (until May 2024) | 2023-07-24 | 13:15 | N/A | Repprted to Rubax via phone. ref: 605146. Engineer will be called out today.
2023-07-24 | 14:00 | Axis | Duxford House Passenger EPL | 21695 M22909 | "Resident just called to advise someone has removed the control panel of the lift" | Rachel | Resolved |  | Rubax (until May 2024) | 2023-07-24 | 16:10 | N/A | Reported to Rubax via phone - ref: 605217. Advised, Engineer call out asap.
2023-07-28 | 9:49 | Axis | Childerley House Goods/Pass EPGL Odds Lift B | 21687 M22901 | Lift reported has gone down again | Rachel | Resolved |  | Rubax (until May 2024) | 2023-07-28 | 10:02 | N/A | Reported to Rubax via phone. advised lift had been left off as fault with processer and damage to CPU. They are aware. Engineer was called whilst on hold and advised engineer will be returning asap hopefully today. Emailed Axis cc SP
2023-08-02 | 08.22 | Axis | Glenbuck Court | ? | Lift on 1-16 side of Glenbuck has developed intermittent fault where lift at G will not open doors to enter. | Tina | Resolved |  | RJ Lifts | 2023-08-02 | 09.17 | WO 00954862 | Reported to RJ lifts by email. Ref 361898
2023-08-02 | 08.57 | Stuart Pike | Duxford House Passenger EPL | 21695 M22909 | Out of service | Tina | Resolved |  | Rubax (until May 2024) | 2023-08-02 | 09.37 | 607738 | Rubax engineer will aim to visit today ref 607738
2023-08-03 | 9:35 | Axis | Childerley House Goods/Pass EPGL Odds Lift B | 21687 M22901 |  | Rachel | Resolved |  | Rubax (until May 2024) | 2023-08-03 | 9:45 |  | Rubax called engineer whilst on hold. Confirmed engineer is heading over to lift now. Rubax believes that parts were replaced although gone down again, so engineer will be looking today. SP update: The lift is being attended today by a Technical engineer so will know more after his visit.
2023-08-04 | 11:03 | Contact Centre/Tenant | Glenbuck Court | M22919 | Middle lift is out of order | Danny | Resolved |  | RJ Lifts | 2023-08-04 | 12:15
2023-08-07 | 15:43 | Stuart Pike | Croxton House Passenger EPL | 21693 M22907 | "The lift is not working" | Danny | Resolved |  | Rubax (until May 2024) | 2023-08-07 | 17:20 | RX 3208 | Reported to Rubax via phone, engineer will attend tonight
2023-08-08 | 7:51 | Stuart Pike | Duxford House Passenger EPL | M22909 | "The lift is not working" | Sarah | Resolved |  | RJ Lifts | 2023-08-08 | 8:51 |  | Reported to Rubax via phone, engineer with attend today. SP 10/08 called Rubax to chase and they had no record of this so reported again under ref : 608113.
2023-08-08 | 13:30 | Axis | Impington House Passenger EPL | 21692 M22906 | "Lift not responding" | Danny | Resolved |  | Rubax (until May 2024) | 2023-08-08 | 14:20 | 608009 | Reported to Rubax via phone, engineer will attend today
2023-08-09 | 10:10 | Axis | Glenbuck Court | M22919 | "Lift door slams when closing, also light in lift not working" | Danny | Resolved |  | RJ Lifts | 2023-08-09 | 10:50 | WO 0095 5390 | Reported to RJ lifts by email.
2023-08-10 | 11:07 | Stuart pike | Duxford House Passenger EPL | 21695 M22909 | Lift not working | Tina | Resolved |  | Rubax (until May 2024) | 2023-08-10 | 11:07 | 608113 | Reported to Rubax. Eng to attend today
2023-08-14 | 07.55 | Aaron Povey | Duxford House Passenger EPL | 21695 M22909 | Stuck on 3rd floor |  | Resolved |  | Rubax (until May 2024) | 2023-08-14 | 07.55 | RX3261 | Aaron Povey reported fault direct to Rubax
2023-08-15 | 16:33 | Axis | Graveley House Goods/Pass EPGL Odds Lift | 21690 M22904 | call from the fire brigade stating there are currently one adult and one child stuck on the lift. They have tried and failed to open the doors and requesting immediate assistant from our lift specialists. | Rachel | Resolved |  | Rubax (until May 2024) | 2023-08-15 | 16:52 | 608451 | All ready reported at 16:40. Engineer is on way asap, is one hour away. Update - 18/8 Rubax call centre said the parts are due in shortly. They need to be installed by two engineers so they hope to have the repair completed before next Wednesday. They are unable to give an exact day at this time.
2023-08-16 | 07.25 | Aaron Povey | Graveley House Goods/Pass EPGL Evens Lift | 21691 M22905 | Not working | Tina | Superseded |  | Rubax (until May 2024) | 2023-08-16 | 07.25 | RX3276 | Aaron Povey reported fault direct to Rubax
2023-08-16 | 07.25 | Aaron Povey | Duxford House Passenger EPL | 21695 M22909 | Not working | Tina | Resolved |  | Rubax (until May 2024) | 2023-08-16 | 07.25 | RX3277 | Aaron Povey reported fault direct to Rubax
2023-08-19 | 15:05 | Tenant (Andrei Mihaita ) | Cumberland House 45/84 Centre | M22918 | Lift stuck on ground floor | Danny | Superseded |  | RJ Lifts |  | 15:05 | 364501 | Reported to RJ lifts over the weekend. Lift is currently out of order
2023-08-21 | 11:00 | John Meacock | Cambridge Gardens Estate 67/102 CENTRE | M22913 | Broken lift button | Danny | Resolved |  | RJ Lifts | 2023-08-21 | 13:50 | WO 0095 6077 | Reported to RJ lifts by email.
2023-08-23 | 07.48 | OOH report | Cumberland House 45/84 Centre | M22918 | Not working | Danny | Resolved |  | RJ Lifts | 2023-08-23 | 07.48 | Report/Job No 364501 | OOH team reported fault to RJ Lifts. 30/08/2023 email update requested from RJ Lifts by Dave H. Currently out of serivce. awaiting parts, quote resent to Paul Dunkerton 30/08/2023 as Stuart is on annual leave. Dave H spoke to RJ Lifts around lunchtime 4/9/23 and was informed that someone would call him back with an update. No call has been forthcoming. 08/09/2023: Report from RJ Lifts - "centre and south lifts our of serivce awaiting parts" SP 02/10 Discussed this with RJ. They attended on 23/08 and one of the control boards was water damaged. A quote was raised and the new board was replaced and the lift was put back into service on 11/09.
2023-08-23 | 15:21 | Tom Dalton | Dowler Court | TBA | The alarm is randomly sounding | Danny | Resolved |  | RJ Lifts | 2023-08-24 | 10:05 | WO 0095 6296 | Reported to RJ lifts via email
2023-08-24 | 9:41 | Caretaker/Stuart Pike | Duxford House Passenger EPL | 21695 M22909 | Lift is still out of order | Danny | Superseded |  | Rubax (until May 2024) | 2023-08-24 | 10:20 | Lift Ref 21695 M22909 Fault Ref 608 924 | Reported to Rubax by phone. 30/08/23 reported as not working. 30/8/23 Dave H spoke to Rubax who are sending another engineer back to site today. UPDATE 31/08/23 - needed matresses and fridges removed - all done and engineer on site as of 3pm
2023-08-26 |  | OOH report | Madingley House Goods/Pass EPGL Evens Lift | 21688 M22902 | Lift is out of order | Danny | Superseded |  | Rubax (until May 2024) | 2023-08-26 | 12:30 | Lift ref 21688 M22902 Fault Ref 609 007 - RX3409 | Reported to Rubax by phone. 30/08/23 evens not Working, Odds Working. Axis electrician has re-instated the supply but lift is still saying out of order. 30/8/23 Dave H spoke to Rubax who confirmed that now the power has been reinstated they will now return to site. Engineer will attend today 31/08/23 (DC)
2023-09-04 | 7:56 | Aaron Povey | Duxford House Passenger EPL | 21695 M22909 | Lift not working | Dave | Superseded |  | Rubax (until May 2024) | 2023-09-04 | 10:00 |  | Reported to Rubax by phone who were already aware of fault 05/09/2023 Reported by Estates Officer as still stuck on the second floor. Dave H spoke to Rubax at 9am, Engineer is going back to site today, time tba. 07/09/2023: Daily report from Estates Manager lists duxford/shelford as not working.
2023-09-04 | 7:56 | Aaron Povey | Croxton House Passenger EPL | 21693 M22907 | Lift not working | Dave | Superseded |  | Rubax (until May 2024) | 2023-09-04 | 10:00 |  | Reported to Rubax by phone who were already aware of fault. 05/09/2023 Reported by Estates Officer as still stuck on the second floor. Dave H spoke to Rubax at 9am, operator will call back with an update as they couldn't get through to the Engineer. 07/09/2023: Daily report from Estates Manager lists harston/croxton as not working.
2023-09-04 |  | Axis | Cambridge Gardens Estate 125/160 EAST | M22915 | Lift out of service | Rachel | Resolved |  | RJ Lifts | 2023-09-05 | 10:30 | WO00956974 RJL ref 371133 | 05/09/2023 Reported to RJ Lifts via email. CC's SP PD LP & Axis CC. 05/09/2023: Report from RJ Lifts: "Upon arrival found the lift in serivce, after investigation found the lift intermittently faulting car gate contact, adjusted and cleaned, advise car gate contacts to be replaced, run and tested, lift left in serivce"
2023-09-05 | 11:03 | Axis | Glenbuck Court | M22919 | Doors wouldn’t open until lift called back up to the 1st floor. Ongoing problem for several weeks, possible related issue RJ Lifts ref 361898 2/8/23. | Dave | Resolved |  | RJ Lifts | 2023-09-05 | 11.43 | WO00956980 RJ Lifts Ref 371153 | 05/09/2023 Reported to RJ Lifts via email. CC's SP PD LB Bus Support. 05/09/2023: From RJ Lifts report: "either, checked all 3 lifts with no faults occurring, tested continually, lift left in serivce".
2023-09-06 | 06.38 | Aaron Povey | Graveley House Goods/Pass EPGL Odds Lift | 21690 M22904 | Stuck on 9th floor | Tina | Superseded |  | Rubax (until May 2024) | 2023-09-06 | 08.29 | Ref RX3474 | Rubax ref number RX3474. Rubax unsure when engineer will attend 6/9 or 7/9 07/09/2023: Daily report from Estates Manager lists Graveley odds as not working. 08/09 update from Rubax - lift is off due to the water leak in the lift shaft. Water seeping into the pit and contaminating the equipment. Fault can't be dealt with until water is pumped out which is not Rubax's responsibility.
2023-09-06 | 10:22 | Axis | Cambridge Gardens Estate 105/124 NORTH | M22914 | Lift Out of Service | Dave | Resolved |  | RJ Lifts | 2023-09-06 | 11:06 | WO00957083 RJ Lifts Ref 371317 | 06/09/2023 Reported to RJ Lifts via email. CC's SP PD LP & Axis CC.
2023-09-06 | 12:05 | Paul Dunkerton | Cumberland House 85/120 North | M22931 | Lift Out of Service for approx two weeks | Dave | Resolved |  | RJ Lifts | 2023-09-05 | 11:00 | Report/Job No 371650 | RJ Lifts informed DH on 5/9 then North was out of Service but RBK were not previously aware. 6/9/23 PD (RBK) has sent a letter to affected residents as follows: The lift engineers have attended and it is currently out of service due to a fault on the drive inverter which now requires replacing. Unfortunately this is a complex repair which will require parts to be sent to a specialist contractor to remove all the parameters from the old drive and transfer to the new drive. 08/09/2023 - report received from RJ Lifts: "Upon arrival found the lift in service, the lift has been mistakenly reported as out of serivce due to a misunderstanding of what lifts have been left out of service on site". RBK correctly reported at the time which lifts were affected. 21/09/2023 Update from RJ Lifts: Planned attendance on 28/09/2023. SP 02/10 I discussed this with RJ and when they arrived on site this lift was working on arrival no fault found.
2023-09-07 | 12:06 | Axis | Glenbuck Court | M22919 | Lift not working. it appears that the lift buttons are faulty. | Dave | Resolved |  | RJ Lifts | 2023-09-07 | 13:51 | WO00957191 | 07/09/2023 Reported to RJ Lifts via email. CC's SP PD LB & Axis CC. 07/09/2023 13:51: RJ Lifts have informed us that the lift has been 'isolated'. 13/09/2023 Chaser email sent to RJ Lifts cc PD, SP. 14/09/2023: 11.45 am urgent escalation by SP of RBK, awaiting update. 14/09/2023: update from PD RBK 15:55 - lift engineers are back on site tomorrow (15/9) they can't seem to find the fault. 15/09/2023: RJ Lifts found break intermittently not lifting causing motion failure. Replaced BR contactor as faulty. Tested for remainder of day left in service
2023-09-07 | 15:31 | Axis | Madingley House Goods/Pass EPGL Evens Lift | 21688 M22902 | Serious fault occurs at floor 12, deemed to be dangerous | Dave | Resolved |  | Rubax (until May 2024) | 2023-09-07 | 15:50 | 611745 | 07/09/2023 Reported to Rubax by phone, they will assign an engineer. From resident: "lift drops at floor 12 and stalls and says lift out of service before dropping again, then continuing down".
2023-09-08 | 6:31 | Aaron Povey | Duxford House Passenger EPL | 21695 M22909 | Update from Rubax Key Accounts Administrator 11/09/2023 | Dave | Resolved |  | Rubax (until May 2024) | 2023-09-08 | 10:00 | 611567 | 04/09 – job with engineer, will attend today. Will update further tomorrow. 05/09 – lift left isolated as the lifts have been damaged by misuse, repair team required to realign car doors, return visit to be arranged. 06/09 – The lift at Duxford is back in service. The problem is that someone is interfering with the landing doors. The last 2 call outs have been due to the lift doors being forced open while the lift is in motion, which stops the lift and puts it in error. The doors need to be reset and the controller fault cleared. 07/09/2023: Daily report from Estates Manager lists duxford/shelford as not working. 08/09: Update from Rubax - A technical visit is needed and this is happening today. Our tech is due to be on site shortly. 11/09: Update from rubax - lift now returned to service
2023-09-08 | 18.41 | OOH report | Impington House Passenger EPL | 21692 M22906 | Out of service | Tina | Superseded |  | Rubax (until May 2024) | 2023-09-08 |  | RX3501 | Reported by OOH team - Fire brigade have attended and escorted wheel chair tenant up to their flat and will speak to rubax direct as entire estate is affected
2023-09-08 | 18.41 | OOH report | Croxton House Passenger EPL | 21693 M22907 | Out of service | Tina | Superseded |  | Rubax (until May 2024) | 2023-09-08 |  | RX3502 | No notes on OOH report. Update from Rubax 8/9: Croxton is out of service due to misuse of the equipment. A quotation has been issued for the required repairs, awaiting approval.
2023-09-08 | 19.14 | OOH report | Graveley House Goods/Pass EPGL Evens Lift | 21691 M22905 | Evens lift. Door not closing | Tina | Resolved |  | Rubax (until May 2024) | 2023-09-08 |  | RX3502 | On going issue. Evens lift on OOH reported but notes say odd lift 'Odd lift has ongoing issue/ ref: rx3502'
2023-09-09 | 11.26 | OOH report | Impington House Passenger EPL | 21692 M22906 | Out of service | Tina | Superseded |  | Rubax (until May 2024) | 2023-09-09 |  | RX3514 | No notes on OOH report
2023-09-09 | 21.55 | OOH report | Graveley House Goods/Pass EPGL Odds Lift | 21690 M22904 | Both lifts out of order. Reported by flat 55. Resident husband is vulnerable due to poor health and is waiting on the ground floor | Tina | Superseded |  | Rubax (until May 2024) | 2023-09-09 |  | RX3532 | Ref - rx3532 - advised rubax call handler for engineer to call resident with an eta as resident husband is vulnerable and in poor health, cannot climb to floor 14. Rubax update 08/09: Lift is off due to a water leak in the building.Water is seeping into the pit and contaminating the equipment.
2023-09-10 | 09.41 | OOH report | Impington House Passenger EPL | 21692 M22906 | Lift has stopped working again - lift out of service - reported by flat 38 - m22906 | Tina | Superseded |  | Rubax (until May 2024) | 2023-09-10 |  | RX3540 | RX3540 18:51 as per rubax operative has left lift out of service parts required reported 17:52
2023-09-10 | 10.13 | OOH report | Graveley House Goods/Pass EPGL Odds Lift | 21690 M22904 | Both lifts out of service. As reported by flat 27 | Tina | Superseded |  | Rubax (until May 2024) | 2023-09-10 |  | RX3541 | Rx3541/rx3542 - 11:55 am - councillor olly wehing called in to report both lifts out of order.
2023-09-11 | 12:24 | John Meacock | Graveley House Goods/Pass EPGL Evens Lift | 21691 M22905 | Lift out of Service | Dave | Resolved |  | Rubax (until May 2024) | 2023-09-11 |  | 611877 | Reported to Rubax by phone, new job raised.
2023-09-12 | 9:12 | Aaron Povey | Graveley House Goods/Pass EPGL Evens Lift | 21691 M22905 | Daily Update from Estates Team. Not working, water damage | Dave | Resolved |  | Rubax (until May 2024) | 2023-09-12 |  |  | 12/09/2023 Rubax reported that lift is now back in service at 13:28 hours 13/09/2023 Estates Manager has visited lift today and confirmed. Incorrect information provided to RBK yesterday.
2023-09-12 | 9:12 | Aaron Povey | Graveley House Goods/Pass EPGL Odds Lift | 21690 M22904 | Daily Update from Estates Team. Not working, water damage | Dave | Superseded |  | Rubax (until May 2024) | 2023-09-12 |  |  | 12/09/2023 Rubax reported that lift has around 50mm of water in the pit now. We need to get this leak stopped and the pit cleared. All pit wiring is now under water. 13/09/2023 Estates Manager has visited lift today and confirmed. Incorrect information provided to RBK yesterday. 26/09/2023 Estates Manager reported that lift is still not working
2023-09-12 | 9:12 | Aaron Povey | Croxton House Passenger EPL | 21693 M22907 | Daily Update from Estates Team. Not working, no power | Dave | Resolved |  | Rubax (until May 2024) | 2023-09-12 |  |  | Update from Rubax 8/9: Croxton is out of service due to misuse of the equipment. A quotation has been issued for the required repairs, awaiting approval. 12/09/2023 Rubax reported that lift is now back in service at 14:54 hours
2023-09-12 | 9:12 | Aaron Povey | Impington House Passenger EPL | 21692 M22906 | Daily Update from Estates Team. Not working, stuck on 3rd floor | Dave | Resolved |  | Rubax (until May 2024) | 2023-09-12 |  |  | 12/09/2023 Rubax reported that lift is now back in service at 15:23 hours 20/09/2023 Rubax lift breakdown report received. Engineer remarks form 13/09/23 top floor landing rollers had come out of car skate adjusted made to rollers and tested lift returned to service
2023-09-16 |  | Rubax | Childerley House Goods/Pass EPGL Evens Lift A |  | Stop button turned off. Odds or Evens Lift not specified. | Dave | Resolved |  | Rubax (until May 2024) | n/a |  |  | Lift was found with the stop button turned off, tested and lift returned to service. Retrospective report from Rubax 18/09/2023.
2023-09-18 | 11:10 | John Meacock | Chippenham House | M22911 | The lift call button is missing from the lift at Chippenham and needs replacing on the ground floor | Tina | Resolved |  | RJ Lifts | 2023-09-18 | 14.18 | 18/09/2023 - Work order raised and emailed to RJ - ref number 373337 18/09/2023 Engineer visit found lift button vandalised New required Dewhurst us91 complete with up arrow and mountings Button working at present. Left lift in service | 18/09/2023 - Work order raised and emailed to RJ - ref number 373337 18/09/2023 Engineer visit found lift button vandalised New required Dewhurst us91 complete with up arrow and mountings Button working at present. Left lift in service
2023-09-19 | 16:54 | Rubax | Brinkley House Goods/Pass EPGL Odds Lift | 21684 M22898 | Rubax OOH Report - RU21684 | Dave | Resolved |  | Rubax (until May 2024) | n/a | n/a | RU21684 | Rubax comments 'awaiting attendance'. Caretaker apparently called Rubax as the lift is in service but showing the wrong floor on the display. We are unsure from their report if it is the Odds or Evens lift that is affected. 20/09/2023 - An engineer will be attending today 20/09/2023 report email received from Rubax engineer attended, awaiting update. Lift is in service
2023-09-20 | 10.30 | Axis | Cambridge Gardens Estate 105/124 NORTH | M22914 | Lift says out of service and seems to be stuck on the 4th floor. Lift has been out all weekend | Tina | Resolved |  | RJ Lifts | 2023-09-20 | 11.30 | WO 00958560 RJ ref 373654 | 20/9/23 Work order raised and emailed to RJ - ref number 373654 21/09/2023 - Incorrect ref number provided, this is for M22913 for centre lift 67-104. Email to RJL 13:20 asking whether we need to raise another W/O given that the lift location was appended to the order. 21/09/2023 report received from RJ Lifts: 20/09/2023 20:18:21 - Upon arrival found the lift out of serivce, after investigation found the car door gear had faulted, adjusted and performed a door gear re learn, found door close button on the cop broken again (APR cop repair required as fixing stud has snapped) tested the lift with no further faults, lift left in serivce
2023-09-20 | 12:38 | Tom Dalton | Dowler Court | TBA | Alarm is randomly sounding, reoccurance of fault from 23rd August WO 0095 6296. | Dave | Resolved |  | RJ Lifts | 2023-09-20 | 13:30 | WO 00958578 RJ Lift Ref 373701 | 20/9/23 work order raised, emailed to RJ lifts cc SP,PD,LB. 20/09/2023 20:21:08 RJ Lifts Report - Upon arrival found the lift in serivce at the ground floor, no faults present, suspect alarm is a self test from the auto dialler, tested the lift continually with no faults occurring, lift left in serivce
2023-09-21 | 07.45 | Aaron Povey | Impington House Passenger EPL | 21692 M22906 | Lift stuck on 3rd floor | Dave | Resolved |  | Rubax (until May 2024) | 2023-09-21 | 08.30 | Rubax ref 612379 | 21/09/2023 Called Rubax ref 612379 21/09/2023: Update from Rubax - Water in the pit caused damage to wiring, lift left in service.
2023-09-21 | 07.45 | Aaron Povey | Madingley House Goods/Pass EPGL Evens Lift | 21688 M22902 | Evens stuck on 2nd floor | Dave | Resolved |  | Rubax (until May 2024) | 2023-09-21 | 08.30 | Rubax ref 612378 | 21/09/2023 Called Rubax ref 612378 21/09/2023: update from Rubax - The 2 faulty power supplies to the lift motor room have blown. RH no electric to lift and motor room, customer to investigate and get an electrician to site to investigate. RH lift out of service LH lift in service
2023-09-21 | 8:11 | Residents Assoc GC via Stuart Pike | Glenbuck Court | M22919 | Centre Lift - not working, assumed to be due to heavy rainfall last night. | Tina | Resolved |  | RJ Lifts | 2023-09-21 | 09.10 | WO00958637 RJ refs 373811 and 373954 | 21/09/2023 emailed RJ work order number. RJ ref number 373811. Further ref provided by email at 17:28 373954. We have no indication if this is a new fault or for the same occurence. 22/09/2023: Report from Rubax re 373811 - 22/09/2023 15:57:12 Attended site and removed drive unit, went direct to drive specialist, On testing found IGBT failed on U and W out put phases from drive, Drive was repaired on site and tested, Returned to site fitted and tested left in service
2023-09-21 | 20:31 | Axis OOH Report | Croxton House Passenger EPL | 21693 M22907 | LIFT OUT OF SERVICE REPORTED BY Flat 27 Oakington KT1 3JF | Dave | Resolved |  | Rubax (until May 2024) | n/a | n/a | REF: RX3620 | Axis OOH Report
2023-09-22 | 09.10 | John Meacock | Graveley House Goods/Pass EPGL Evens Lift | 21691 M22905 | Stuck on the 14th floor comes down to the 12th and then back up to the 14th with the message lift out of service | Tina | Superseded |  | Rubax (until May 2024) | 2023-09-22 | 09.20 | Ref 612444 | 22/09/2023 Ref 612444 engineer will aim to be onsite today
2023-09-22 | 15.40 | Stuart Pike | Madingley House Goods/Pass EPGL Odds Lift | 21689 M22903 | Power to the Right hand Odds lift has been restored but it will not move unless the button inside the lift is held permanently. | Tina | Resolved |  | Rubax (until May 2024) | 2023-09-22 | 16.15 | Ref 612489 | 22/09/2023 Ref 612489
2023-09-25 | 8:03 | Aaron Povey | Impington House Passenger EPL | 21692 M22906 | Estates Officer Reported this morning that lift is out of service on the 3rd floor | Dave | Resolved |  | Rubax (until May 2024) | 2023-09-25 | 9:40 | Ref 612519 | 25/09/2023 Ref 612519 Rubax report engineer attending Monday evening. Report from Rubax same day: adjusted top floor magnets and upper limit ramp, lift left in service
2023-09-26 | 11:29 | Stuart Pike | Graveley House Goods/Pass EPGL Evens Lift | M22905 | Urgent - Water is cascading down inside the lift car. Rubax who will need to attend and isolate the lift while the source of the leak is found and repaired. | Dave | Superseded |  | RJ Lifts | 2023-09-26 | 11:50 | Ref 612676 | 26/9/23 Ref 612676
2023-09-26 | 9:00 | John Meacock | Fordham House/Connington | M22910 | the lift flooring at Fordham CRE is lifting and needs replacing Possible trip hazzard | Rachel | Resolved |  | RJ Lifts | 2023-09-26 | 9:10 | WO00958984 RJ ref 375104 | 26/09/2023 WO raised and reported RJ. Others cc'd. 26/09/2023 Engineer site visit - Upon arrival found the lift in serivce, found the lift rubber flooring starting to lift in the middle, temp fix made with spray adhesive, advise flooring to be replaced L 1530mm W 1055mm, lift left in serivce
2023-09-26 | 13:55 | Axis | Cambridge Gardens Estate 67/102 CENTRE | M22913 | Resident has reported the central lift is not working and says ‘Out Of Service’, | Dave | Resolved |  | RJ Lifts | 2023-09-26 | 15:19 | WO00959063 RJ Lifts Ref 375183 | 26/09/2023 WO raised and reported RJ. Others cc'd. 27/09/2023 Engineer site visit - Upon arrival found the lift out of service, after investigation found the landing doors not operating, swapped door gear boards with the west lift to test and found it failed again, new door gear board required, lift left out of serivce 28/09/2023: Fitted new door board. Adjusted. Tested left lift in service. Door close button has been vandalised.
2023-09-27 | 10.2 | Stuart Pike | Graveley House Goods/Pass EPGL Evens Lift | 21691 M22905 | Ongoing issue following water leaks | Dave | Resolved |  | Rubax (until May 2024) | 2023-09-27 | 10:20 | Ref 612726 | 27/09/2023 Ref 612726 27/09/2023 - Leaks have been stopped in Graveley and both of the lift pits have been pumped out. Lift contractor Rubax requested to attend and investigate. Awaiting updates from Rubax on when both lifts can be put back into service. 27/09/2023 16:39 Update from Rubax - RH Lift is back in service now there is no water in the pit.
2023-09-27 | 10.20 | Stuart Pike | Graveley House Goods/Pass EPGL Odds Lift | 21690 M22904 | Ongoing issue following water leaks | Dave | Resolved |  | Rubax (until May 2024) | 2023-09-27 | 10:20 | Ref 612726 | 27/09/2023 Ref 612726 27/09/2023 - Leaks have been stopped in Graveley and both of the lift pits have been pumped out. Lift contractor Rubax requested to attend and investigate. Awaiting updates from Rubax on when both lifts can be put back into service. 27/09/2023 16:39 Update from Rubax - LH lift has been left off due to water damage, waiting for it to dry out. Return visit required. 28/09/2023 Engineer still onsite SP 02/10 both lifts were put back into service 28/09
2023-09-29 | 08.04 | Anthonia Shodiya | Duxford House Passenger EPL | 21695 M22909 | Lift stuck on ground floor | Tina | Resolved |  | Rubax (until May 2024) | 2023-09-29 | 08.30 | RX3675 | 29/09/2023 Reported to Rubax ref RX3675 29/09/2023 at 09.34 Anthonia has reported lift has started working again, seems temperamental but working. Please cancel the order. Now cancelled with Rubax
2023-09-29 | 08.04 | Anthonia Shodiya | Chippenham House | M22911 | Lift button (Ground floor) to be replaced | Tina | Resolved |  | RJ Lifts | 2023-09-29 | 08.45 | WO 00959318 | 29/09/2023 Work order raised and emailed to RJ 29/09/2023 RJ emailed that they are aware of this fault as noted on a engineer service visit 04/10/2023: Daily CRE report lists lift as in service
2023-09-29 | 08.04 | Anthonia Shodiya | Croxton House Passenger EPL | 21693 M22907 | Lift stuck on ground floor | Tina | Superseded |  | Rubax (until May 2024) | 2023-09-29 | 18.36 | RX3669 | 29/09/2023 Rubax said this has already been reported by OOH team at 18.39 on Thursday at 28/9
2023-09-29 | 14:09 | Stuart Pike/ Olly Wehring | Croxton House Passenger EPL | 21693 M22907 | As of 13.40 today, the lift is moving from floor to floor but the doors are not opening. | Dave | Superseded |  | Rubax (until May 2024) | 2023-09-29 | 14:33 | Ref 612890 | New callout requested. 29/09/2023: Rubax update (GL) - Engineer has already been and left it in service. Lift out of order because the doors have been held open and have locked out.
2023-10-02 | 09:16 | Aaron Povey | Croxton House Passenger EPL | 21693 M22907 | Stuck on Ground floor - door not opening | Dave | Superseded |  | Rubax (until May 2024) | 2023-10-02 | 12:12 | ref 614165 | New callout requested. I referred to Friday's previous callout on the call. 03/10/2023: CRE Lifts Daily Report states that door is still not opening on the ground floor
2023-10-02 | 17:01 | Axis OOH Report | Graveley House Goods/Pass EPGL Odds Lift | 21690 M22904 | Both Lifts Out of Service. | Dave | Superseded |  | Rubax (until May 2024) | 2023-10-02 | Unknown | RX3711 | Reported by Flat 27. Axis OOH Report received by BS 03/10/2023
2023-10-02 | 17:01 | Axis OOH Report | Graveley House Goods/Pass EPGL Evens Lift | 21691 M22905 | Both Lifts Out of Service. | Dave | Superseded |  | Rubax (until May 2024) | 2023-10-02 | Unknown | RX3712 | Reported by Flat 27. Axis OOH Report received by BS 03/10/2023
2023-10-03 | 07:42 | Aaron Povey | Graveley House Goods/Pass EPGL Odds Lift | 21690 M22904 | Reported by Estates Manager 03/10/2023 | Dave | Superseded |  | Rubax (until May 2024) | Unknown | Unknown | ref RX3719 | 03/10/2023 Ref CRE Lifts Daily Report sent to Business Support. 03/10/2023 - Letter to be issued by RBK shortly to all Graveley residents today explaining the situation and to contact their Housing Officer should they require assistance at this time. All parties informed including Councillors, Axis, Housing Officer and Senior RBK Managers. 03/10/2023 Evening - Lift now back in service
2023-10-03 | 07:42 | Aaron Povey | Graveley House Goods/Pass EPGL Evens Lift | 21691 M22905 | Reported by Estates Manager 03/10/2023 | Dave | Superseded |  | Rubax (until May 2024) | Unknown | Unknown | ref RX3720 | 03/10/2023 Ref CRE Lifts Daily Report sent to Business Support. 03/10/2023 - Letter to be issued by RBK shortly to all Graveley residents today explaining the situation and to contact their Housing Officer should they require assistance at this time. All parties informed including Councillors, Axis, Housing Officer and Senior RBK Managers. 03/10/2023 Evening - Lift now back in service
2023-10-03 | 18:13 | Stuart Pike | Croxton House Passenger EPL | 21693 M22907 | 09/10/2023: reported by Estates Team as working |  | Resolved |  | Rubax (until May 2024) | 2023-10-03 | 18:15 | Ref RX3724 | VERY URGENT as reported to SP via Ed Davey MP 04/01/2023 @16:57 Rubax update received - Lift is switched off, new door operator arm fixings, also detector edge lead damaged. Will advise of next steps once parts established. 06/10/2023: Rubax update - Lift off, damage to the door. Due for repair 07/10/2023 07/10/2023: Rubax update - supplied new door fixings and set up doors. Lift left in service 09/10/2023 Daily update from Estates Officer, reported as now working.
2023-10-04 | 10:23 | John Meacock | Graveley House Goods/Pass EPGL Evens Lift | 21691 M22905 | Lift is stuck on the ground floor with the doors open and a barrier in front | Dave | Resolved |  | Rubax (until May 2024) | 2023-10-04 | 10:57 | Ref 615115 | Reported to Rubax. 04/10/23 @16:36 Rubax report received - lifts returned to service following the pit being pumped
2023-10-04 | 10:23 | John Meacock | Graveley House Goods/Pass EPGL Odds Lift | 21690 M22904 | Working but no lighting | Dave | Resolved |  | Rubax (until May 2024) | 2023-10-04 | 10:57 | Ref 615115 | Reported to Rubax. 04/10/23 @16:36 Rubax report received - lifts returned to service following the pit being pumped
2023-10-05 | 13:40 | Stuart Pike | Graveley House Goods/Pass EPGL Odds Lift | 21690 M22904 | 09/10/2023: reported by Estates Team as working | Dave | Resolved |  | Rubax (until May 2024) | 2023-10-05 | 14:13 | Ref 615174 | Estates Officer was in this lift when it suddenly dropped about 1 foot. Also lift is now stopping on the Mezz Floor. 05/10/2023 Update from Rubax: Engineer to attend. Lift out of service pending follow on works. Lift working but skate is clipping on 13th floor. Repair works complete and lift left in service 06/10/2023: Update from Rubax: Due for further inspection on 7/10/23 09/10/2023 Daily update from Estates Officer, reported as now working.
2023-10-09 | 10:05 | Stuart Pike | Brinkley House Goods/Pass EPGL Odds Lift | 21684 M22898 | LIft temporarily out of service. | Dave | Resolved |  | Rubax (until May 2024) |  |  |  | 09/10/2023: A deep clean is taking place in the lift motor room as the door to the roof was off its hinges for a while . A lift engineer is in attendance at the block assisting the cleaning team. 10/10/2023 Daily update from Estates Officer, reported as now working.
2023-10-09 | 10:05 | Stuart Pike | Brinkley House Goods/Pass Evens Lift EPGL | 21685 M22899 | LIft temporarily out of service. | Dave | Resolved |  | Rubax (until May 2024) |  |  |  | 09/10/2023: A deep clean is taking place in the lift motor room as the door to the roof was off its hinges for a while . A lift engineer is in attendance at the block assisting the cleaning team. 10/10/2023 Daily update from Estates Officer, reported as now working.
2023-10-10 | 07:26 | Aaron Povey | Graveley House Goods/Pass EPGL Evens Lift | 21691 M22905 | Evens lift stuck on mezzanine floor | Dave | Resolved |  | Rubax (until May 2024) | 2023-10-10 | 8:56 | 615301 | 10/10/2023 Daily update from Estates Officer, reported as stuck on mezzanine floor 10/10/23: Update from Rubax - engineer to attend site. Problem was due to engineers pumping water out of the pits 11/10/2023 Daily update from Estates Officer, reported as now working.
2023-10-10 | 9:55 | Stuart Pike | Madingley House Goods/Pass EPGL Odds Lift | 21689 M22903 | Problems with lift, stuck on the 13th floor | Rachel | Resolved | 2023-10-17 | Rubax (until May 2024) | 2023-10-10 | 10:30 | 615317 | 10/10/2023: Madingley odds lift the door tried to shut 3 times unsuccessfully on the 13th floor and will abruptly jolt either on floor 8 or 12 then say out of service, rock about then continue on. . 10/10/23: Update from Rubax - engineer to attend site. 11/10/23: Update from Rubax -Lift has a fault with the doors which are jammed up. Repair team needed. 11/10/2023 Stuart chased Rubax - Engineer can not get the lift away from the floor to investigate the fault. Rubax will send a team asap. Unable to move landing doors, second engineer required to manually move lift to complete door repair. Lift left isolated 16/10/2023 Daily update from Estates Officer, odds lift reported as still stuck on the 13th floor. 16/10 – attendance tomorrow as they are still on another site. 17/10/2023 Daily update from Estates Officer - now reported as in service
2023-10-16 | unknown | Axis OOH Report | Graveley House Goods/Pass EPGL Evens Lift |  | Lift Out of Service | Dave | Resolved |  |  | n/a | n/a | n/a | Left hand lift is out of service pending follow on works
2023-10-16 | unknown | Unknown | Childerley House Goods/Pass EPGL Evens Lift A | 21686 M22900 | Entrapment | Dave | Resolved | 2023-10-17 | Rubax (until May 2024) | n/a | unknown | RU21686 | 16/10/23: report from Rubax: Entrapment, passengers released and tested lift left in service.
2023-10-17 | 13:22 | axis | Croxton House Passenger EPL | 21693 M22907 | Lift out of service | Rachel | Resolved | 2023-10-18 | Rubax (until May 2024) | 2023-10-18 | 13:35 | 615709 | 17/10/2023 lift being out of service and not moving: The resident at Flat 27 Oakington KT1 3JF called this in. Rubax To raise with operative asap and attend site today. 18/10/23 - Estates Officer reported lift as now in service
2023-10-18 | 07:52 | Aaron Povey | Cambridge Gardens Estate 105/124 NORTH | M22914 | Lift out of service | Dave | Resolved | 2023-10-19 | RJ Lifts | 2023-10-18 | 8:32 | WO00960696 383212 | 18/10/23 - Estates Officer reported lift lift as out of service - door not opening, lift not moving. Report from RJ Lifts same day, in service. 19/10/2023 - Estates Officer reported lift as in service
2023-10-20 | 07.52 | Aaron Povey | Cambridge Gardens Estate 67/102 CENTRE | M22913 | States out of service | Tina | Resolved | 2023-10-20 | RJ Lifts | 2023-10-20 | 08.10 | WO00960927 383569 | 20/10/2023 Emailed work order to RJ. Breakdown logged at RJ 20/10/2023 Visit report sheet - Upon arrival found the lift out of serivce with no car lighting, after investigation found water ingress into the lift shaft causing the car lighting supply to trip, cleaned water and dried units to be able to re set and return the lift to serivce, re set and returned to service.
2023-10-22 | Not known | OOH ? | Madingley House Goods/Pass EPGL Evens Lift |  | Entrapment | Tina | Resolved | Resolved | Rubax (until May 2024) | 2023-10-22 | Not known | 615910 | 24/10/2023 report email received from Rubax entrapment on Sunday 22/10/223. Not on OOH report.
2023-08-30 | 14:30 | Axis | Cumberland House 1/44 South | M22917 | Lift is out of order - awaiting parts. Lift back in service as at 18/10/23. | Dave | Resolved | 2023-10-24 | RJ Lifts | 2023-08-30 | 15:07 | WO00956623 RJ Lifts ref 369362 WO00958193 RJ Lifts new ref 371650 | Reported to RJ lifts via email. RJ Lifts ref 369362 confirmed 30/08/2023. Lift needs parts which have been ordered and will be put back into service as soon as possible. Approved for go ahead by PD 1pm 31/08. Dave H spoke to RJ Lifts around lunchtime 4/9/23 and was informed that someone would call him back with an update. No call has been forthcoming. 07/09/23 - new reference provided, 371650. 08/09/2023: Report from RJ Lifts - "centre and south lifts our of serivce awaiting parts" 21/09/2023 Update from RJ Lifts: Planned attendance on 28/09/2023 SP 02/10. Discussed this with RJ. Drive board from Europe was due 28/09 but this has been delayed so now due towards the end of w/c 02/10. 06/10 RJ Lifts Report: Removed Drive, dropped to Lester Controls. Planned attendance 08.10.2023. 18/10/2023 RJ lifts report: Upgraded line filter, drive, brake resistor, MC, MC1 and BR contactor. Changed drive settings for auto tune. Completed. Found down reset switch stuck open. Released and lubricated. Power supply unit for door zone loose, connection secured. Adjusted ground to second floor levels. Ran and tested. Left lift in service. Recommend handrail in motor be changed to allow panel door to be opened fully. Landing signs have been changed from ground to seventh. Lift buttons and indicators basement to sixth.
2023-10-23 | 08:33 | Aaron Povey | Madingley House Goods/Pass EPGL Odds Lift | 21689 M22903 | Lift stuck on Ground Floor | Dave | Resolved | 2023-10-24 | Rubax (until May 2024) | 2023-10-23 | 9:12 | 615928 | Reported to Rubax by phone, engineer will be sent to site. 24/10/23 - Estates Officer reported lift as out of service 24/10/23 Engineer attended and found the overspeed governor switch had tripped, he has reset, and is still testing now but the lift should be back in service soon. 24/10/2023 Rubax udpate - Governor tripped, rectified and lift left in service
2023-10-24 | 07:47 | Aaron Povey | Fordham House/Connington | M22910 | Lift vandalised, out of service for 7-10 days. | Dave | Resolved | 2023-11-06 | RJ Lifts | 2023-10-24 | 8:52 | WO00962157 | Reported by email to RJ Lifts cc SP PD LB BS Report received late am 24/10 from RJ Lifts related to callout on 21/10: Found 2nd floor lock set up broken and requires replacement, found skate arm also bent, unable to fully investigate skate as would have been unable to make the landing door safe due to lock set up being broken, please see attached photos, lift has been left out of service. 26/10/23 - Engineer returning onsite today/ 25/10/2023: Quote 80820 provided by RJ Lifts to rectify the above 03/11/23 - Estates Officer reported lift as still stuck on 2nd floor 06/11/23 - Estates Officer reported lift as now in service
2023-10-25 | 10:11 | Stuart Pike | Fordham House/Connington |  |  | Dave | Resolved | 2023-11-03 | RJ Lifts | 2023-10-25 | 10:11 | wo00962251 | 06/11/23 - Estates Officer reported lift as now in service
2023-10-27 | 10:50 | Axis | Madingley House Goods/Pass EPGL Odds Lift | M22903 | Lift out of service - awaiting parts | Dave | Superseded | 2023-10-30 | RJ Lifts | 2023-10-27 | 11.26 | 616194 | Flat 11 Madingley has called to report that the odds lift is out of service again, he was stuck in it last weekend and said an engineer fixed it on Tuesday just gone but says since then it goes really fast sometimes and then gets stuck on the 3rd floor. The resident contact number is 07306891147 incase you need it. 27/10/23 - Reported to Rubax by phone. No update provided by Rubax.
2023-10-30 | 07:48 | Aaron Povey | Madingley House Goods/Pass EPGL Odds Lift | M22903 | Lift Stuck on 7th floor | Dave | Superseded | 2023-11-01 | RJ Lifts | 2023-11-01 | 9:15 | RX3903 new ref: 389172 | 30/10/23 - Report to Rubax by phone. - not resolved.
2023-11-03 | 08:21 | Aaron Povey | Madingley House Goods/Pass EPGL Evens Lift | M22902 | Evens Lift stuck on ground floor | Dave | Resolved | 2023-11-06 | RJ Lifts | 2023-11-03 | 8:52 | 391097 WO00963000 | Aaron reported fault to RJ Lifts by phone. RJ Lifts confirmed with fault reference by email and BS raised a retrospective work order cc PD SP AS AP BS
2023-11-04 |  | OOH | Madingley House Goods/Pass EPGL Evens Lift | M22902 | 3 passengers Trapped on ground floor | Dave | Resolved | 2023-11-06 | RJ Lifts |  |  |  | From RJ Lifts report received today. OOH callout the previous weekend.
2023-11-01 | 07:45 | Aaron Povey | Madingley House Goods/Pass EPGL Odds Lift | M22903 | Lift Stuck on 7th floor. Taken out of service pending further investigation. | Dave | Resolved | 2023-11-07 | RJ Lifts | 2023-11-01 | 8:23 | WO00962782 391066 | 01/11/23 - Estates Officer reported that odds lift is still stuck on the 7th floor 01/11/2023 - new fault raised with RJ Lifts cc SP PD LB BS 01/11/23 - Site report from RJ Lifts: LIFT TURNED OFF Upon arrival found the lift out of service, after inspection found the lift on test via the car top control, found lift drive had tripped also, re set drive and placed lift back into serivce, Upon testing found lift pit flodded with water, conduit submerged, advise pit to be pumped out and water damaged to be assessed, pit buffer wiring to be replaced, new kone car top battery will be required also as the lift has been fully isolated, found FB4 key stuck in ladder cabinet advise lock to be replaced 03/11/23 - Report from RJ Lifts - 1. Carry out assessment of water damaged components and report findings. 2. Supply and fit new car top battery. Please note: further costs may apply if water damaged components require replacement following investigations. 06/11/23: new fault raised with RJ Lifts cc SP PD LB BS 07/11/23 - Estates Officer reported that lift is in service.
2023-11-06 |  | Aaron Povey | Madingley House Goods/Pass EPGL Evens Lift | M22902 | Evens Lift stuck on 2nd floor | Dave | Superseded | 2023-11-08 | RJ Lifts | 2023-11-06 | 9:20 | WO00963125 | 06/11/23: new fault raised with RJ Lifts cc SP PD LB BS 07/11/23 - Estates Officer reported lift still stuck on 10th floor
2023-11-07 | ? | ? | Madingley House Goods/Pass EPGL Evens Lift | M22902 | Evens Lift stuck on 10th floor | Dave | Resolved | 2023-11-10 | RJ Lifts | 2023-11-07 | ? | RJ Lifts Ref 391824 | 07/11/23: RJ Lifts Breakdown Report received at 17:25 hours 08/11/23 - Evens lift has a drive processor fault which indicates issues with the braking system. This requires a specialist company to attend which is in the process of being arranged so will be out for a while yet. 10/11/23 - Estates Officer reported lift as stuck on 10th floor Planned attendance by RJ Lifts 14.11.23 13/11/23 Engineer visit report received -Set up break corre try and tested. Found safety edge leads broken on testing causing doors to remain open. Left off for new panna crome plus leads. On test at top floor. 14/11/2023 CRE spreadsheet confrms lift is working
2023-11-08 | ? | Nicola | Madingley House Goods/Pass EPGL Odds Lift | M22903 | Odds out of service | Dave | Resolved | 2023-11-10 | RJ Lifts | 2023-11-08 |  | RJ Lifts Ref 391824 | Odds Not Working No Power Out Of Service Again. Caller Didn't Know If The Doors Were Closed Or Open Or If The Lift Was Stuck On Any Floor As Call Cut Off. 07/11/23 Upon arrival found the lift out of serivce at the 13th floor, adjusted landing lock tested left in service. 08/11/23 - The odds lift had a door issue (possible misuse ) which required two engineers today to repair. 10/11/23 - Lift tested by Estates Manager this morning as follows: "The lift then started to work again and the residents got out on the ground floor. I've been up to the 15th floor in the odds lift with no problems. I then tested the lift and sent it up to other floors without any problems".
2023-11-07 | 10:25 | Aaron Povey | Graveley House Goods/Pass EPGL Evens Lift | M22905 | Evens Lift stuck on 10th floor | Dave | Resolved | 2023-11-10 | RJ Lifts | 2023-11-07 | 10:52 | WO00963289 RJ Lifts Ref 391656 | 07/11/23: new fault raised with RJ Lifts cc SP PD LB BS 07/11/23 visit report - upon arrival found the lift out of service, landing doors required adjustment but unable to do this alone due to skip floors, assisted by dean faulkner, adjusted and tested continually with no faults lift left in service 10/11/23 - Estates Officer reported lift as in service 13/11/2023 Service visit report received - Arrived on site found both lifts working on. Arrival. Ran and tested both thoroughly and left in service 14/11/2023 SP email - Yesterday Axis successfully fitted the water extraction "sump pumps" into both of the lift pits at Graveley. This will prevent any future build up of water and is definitely something we will consider for the remaining 3 tower blocks.
2023-11-11 | 13.11 | OOH | Graveley House Goods/Pass EPGL Odds Lift | M22904 | Lift not responding when called | Tina | Resolved | 2023-11-11 | RJ Lifts | 2023-11-11 | 13.09 | RJ 392626 | OOH New breakdown logged on Saturday 11/11 lift not responding when called 13/11/2023 SP email reminder that the sump pumps are being fitted today so the odds lift will be out all morning then the evens all afternoon. Note that all residents were sent a letter over a week ago so please do not raise any new faults for these. 13/11/2023 Service visit report received - Arrived on site found both lifts working on. Arrival. Ran and tested both thoroughly and left in service 14/11/2023 SP email - Yesterday Axis successfully fitted the water extraction "sump pumps" into both of the lift pits at Graveley. This will prevent any future build up of water and is definitely something we will consider for the remaining 3 tower blocks.
2023-10-16 | 09:57 | RJ Lifts | Cambridge Gardens Estate 125/160 EAST | M22915 | Lift out of service - awaiting parts | Dave | Resolved | 2023-11-10 | RJ Lifts | 2023-10-23 | 10:45 | 382813 WO00960496 WO00960672 | 16/10/23 emailed RJ lifts cc SP, SP 17/10/2023 - Caretaker called to advise the lift is now completely out of service. Please use him as point of contact when needed, his contact details are Ray Cottee Mobile: 07712399676 . 17/10/2023 - This lift has been taken out of service as the lights inside the lift car have blown. A new unit is required and will probably take a few days before it can be fitted. 22/10/2023 Report from RJ Lifts following site visit: left out of serivce awaiting car lighting replacement and gov solenoid bracket 25/10/23 - Awaiting update from the lift contractor. 26/10/23 - Engineer returning onsite today. 03/11/23 - Report from RJ Lifts: There is a fault with the A3 device, we have ordered the part and this will be fitted on the 7th November. 10/11/23 - Estates Officer reported lift as out of service 14/11/23 SP email - At the time of writing this email all of the lifts at Cumberland Hse, Cambridge Gdns & CRE are currently in service. 16/11/23 Visit report received - Collected correct bracket from Crayford stores and fitted, lift back in serivce
2023-11-08 | 15:55 | Axis | Charles Lesser House | M22923 | Lift is Stuck opposite flat 9. | Dave | Resolved | 2023-11-16 | RJ Lifts | 2023-11-08 | 16:19 | WO00963481 RJ Lifts Ref 392002 | 08/11/23 Resident has reported that lift at Charles lesser is stuck with door open opposite flat 9 and the light also needs fixing 1990 is key safe for engineer main door by letter box . 08/11/23 - problem identified, further visit to site planned 10/11/23 Engineer attended site.New car light upgrade required due to blown ballasts. One bulb is working and the emergency works but don't expect it to be for long. Reduced depth LED unit required from A & A. Spare parts are awaited. 16/11/2023 Visitor report received - Collected parts. Removed old faulty lift car lighting equipment and replaced with new LED light fittings complete with all new wiring and emergency back up. Tested and returned lift back to normal service. Disposed of old fittings in the correct manner
2023-11-17 | 10:34 | Ray Cottee | Cambridge Gardens Estate 125/160 EAST | M22915 | East Wing Lift has broken down again | Dave | Resolved | 2023-11-20 | RJ Lifts | 2023-11-17 | 11:29 | WO00964284 RJ Lifts Ref 393460 | Reported by email to RJ Lifts cc SP PD LB RC AS BS

## Lifts Not Listed
Lifts Not Listed
Grantchester House - Lift has been permanently taken off contract. This is due to the building being demolished in the near future. Do not accept or report any failures on this lift. Ref email from Stuart Pike 09/11/2022
Edinburgh Court Watersplash Cl, Kingston On Thames KT1 2TB - no lift code, refer to Stuart Pike/Paul Dunkerton if a lift fault is received
Oakington - Being maintained by another contractor, Ref Stuart Pike email 03/04/2023

## Lift Contractor Contacts
RJ Lifts
General tel number 24/7 for all enquiries including callouts – 0800 999 1177 or 01782 342225
Email for PO’s and orders (general enquiries) –
rj-kingston@rjlifts.co.uk
or
Enquiries@rjlifts.co.uk
To check if work orders have been received:
Breakdown@rjlifts.co.uk
Enquiries@rjlifts.co.uk
Rubax
Main call centre number 24/7 - 01925 849200 or 0800 7318277
N.B. Purchase order number for all Rubax lift faults : 31014992
Otis
Report faults received by emailing
customerservicespswest@countrysidepartnerships.com
Business Support will log faults on our Lifts Monitoring Spreadsheet.
We will also update Paul Dunkerton’s spreadsheet RBK Defect record sheet for Arun Hse as this contains all defects for this block - all members of Business Support have editing rights.
Arun House will revert to RJ Lifts at the end of the defects period late July 2024.

## input data
List of lift locations and numbers | Lift number | Contractor
Brinkley House Goods/Pass EPGL Odds Lift | M22898 | RJ Lifts
Brinkley House Goods/Pass Evens Lift EPGL | M22899 | RJ Lifts
Childerley House Goods/Pass EPGL Evens Lift A | M22900 | RJ Lifts
Childerley House Goods/Pass EPGL Odds Lift B | M22901 | RJ Lifts
Madingley House Goods/Pass EPGL Evens Lift | M22902 | RJ Lifts
Madingley House Goods/Pass EPGL Odds Lift | M22903 | RJ Lifts
Graveley House Goods/Pass EPGL Odds Lift | M22904 | RJ Lifts
Graveley House Goods/Pass EPGL Evens Lift | M22905 | RJ Lifts
Impington House Passenger EPL | M22906 | RJ Lifts
Croxton House Passenger EPL | M22907 | RJ Lifts
Duxford House Passenger EPL | M22909 | RJ Lifts
Westwick House | M22908 | RJ Lifts
Fordham House/Connington | M22910 | RJ Lifts
Chippenham House | M22911 | RJ Lifts
Cambridge Gardens Estate 17/64 WEST | M22912 | RJ Lifts
Cambridge Gardens Estate 67/102 CENTRE | M22913 | RJ Lifts
Cambridge Gardens Estate 105/124 NORTH | M22914 | RJ Lifts
Cambridge Gardens Estate 125/160 EAST | M22915 | RJ Lifts
Glenbuck Court | M22919 | RJ Lifts
Glenbuck Court | M22920 | RJ Lifts
Glenbuck Court | M22921 | RJ Lifts
Charles Lesser House | M22923 | RJ Lifts
Charles Lesser House | M22924 | RJ Lifts
Fountain Court | M22926 | RJ Lifts
Canbury Court 7/42 | M22932 | RJ Lifts
Gilpin House | M22927 | RJ Lifts
Cumberland House 1/44 South | M22917 | RJ Lifts
Cumberland House 45/84 Centre | M22918 | RJ Lifts
Cumberland House 85/120 North | M22931 | RJ Lifts
Hugh Herland House | AC754 | RJ Lifts
Sobraon House | AC756 | RJ Lifts
Dowler Court | TBA | RJ Lifts
Edinburgh Court | No code | RJ Lifts
Arun House | CR1 - to be confirmed | Otis | To be reported to Countryside Customer Care Team - to be confirmed
Ribble House | YW-1 - to be confirmed | Otis | To be reported to Countryside Customer Care Team - to be confirmed

## Import Range embed sheet - test
Date received | Time Received | Lift location detail | Fault | Status | Last Updated
2023-11-15 | 11:00 | Cumberland House 45/84 Centre | Intermittent fault and doors screech every time the door opens and closes. Lift taken out of service by Lift Contractor 15.11.23 due to faulty car door rollers. RBK has requested that the contractor puts the lift back into service 16.11.23 in the afternoon pending planned attendance to replace the rollers on 20.11.23. Axis Customer Services - please do not raise call outs for this issue until the parts have been replaced. | Outstanding | 2023-11-17
2023-11-21 | 08.55 | Fordham House/Connington | Hole under flooring inside lift and the lift stops on the 2nd floor and jolts, does not go up to the third floor. Lift has been turned off for repair. | Outstanding | 2023-11-22
2023-11-21 | 08.55 | Madingley House Goods/Pass EPGL Evens Lift | Even lift - door opens - however the opening button inside the lift is stuck needs to be rectified. | Outstanding | 2023-11-22